## Sheet1
Name: | Nicholas Cimino |  | Total Time: | 27:28
Date: | General Category: | Starting Time: | Ending Time: | Calculated Time Worked: | Description:
2025-10-03 | Design Draft | 11:17 | 14:39 | 3:22 | Sat down with group after class to define project and talk through all of Design Draft points (Deliverables, Requirements, Division of work, ect.)
2025-10-05 | Design Draft | 15:09 | 20:13 | 5:04 | Completed Introduction of the design draft, Mock-Up for the Systems, and made final revisions of the Design Draft with the group.
2025-10-06 | Check-in | 15:00 | 15:32 | 0:32 | Check-in 1: Met with group & Tyler, discussed our design draft, and asked questions regarding design plan and material buying
2025-10-12 | Logistics | 20:12 | 20:37 | 0:25 | Set-up GitHub updates on the group Discord to record team-members’ commits
2025-10-14 | Check-in | 11:20 | 11:51 | 0:31 | Check-in 2: Met with group & Tyler, reviewed out submitted design draft, discussed adding more hardware specification, and discussed with group members to start buying materials and beginning research
2025-10-18 | Design Plan | 22:09 | 23:39 | 1:30 | Made additions to the Hardware Specifications for the Design Plan and did research for the Bill of Materials in order to specify the hardware used and communication methods used
2025-10-19 | Design Plan | 17:55 | 19:38 | 1:43 | Made final edits to the Design Plan to complete and submit it with the group
2025-10-20 | Technical Research | 13:08 | 14:58 | 1:50 | Reviewed and added to the Bill of Materials and investigated basic Backend development concepts and different Database types and Data Storage structures (settled on MongoDB to store JSON data)
2025-10-20 | Check-in | 15:08 | 15:39 | 0:31 | Check-in 3: Met with group & Tyler, discussed Pre-Alpha Build and what is expected from it, and discussed with group members assignment of tasks and expectations from them for the Pre-Alpha Build.
2025-10-24 | Pre-Alpha Build | 15:12 | 21:17 | 6:05 | Created a skeleton-code backend with express.js and mongoose and a database to test the backend. Ran into issues due to original set up of backend code and MongoDB database not actually locally deployed.
2025-10-25 | Pre-Alpha Build | 11:49 | 17:14 | 5:25 | Updated backend to better organize functionality and finally got a MongoDB database set up locally on my laptop. Added CRUD functions to backend and successfully tested them with browser and Postman.
| Technical Research | 18:24 | 18:54 | 0:30 | Researched how ESP-32 can communicate with Backend in order to send data to the database. Learned HTTP requests over Wifi can be used by ESP-32 with JSON format data to communicate with backend API.
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00