## Sheet1
Name: | Nicholas Cimino |  | Total Time: | 40:51
Date: | General Category: | Starting Time: | Ending Time: | Calculated Time Worked: | Description:
2025-10-03 | Design Draft | 11:17 | 14:39 | 3:22 | Sat down with group after class to define project and talk through all of Design Draft points (Deliverables, Requirements, Division of work, ect.)
2025-10-05 | Design Draft | 15:09 | 20:13 | 5:04 | Completed Introduction of the design draft, Mock-Up for the Systems, and made final revisions of the Design Draft with the group.
2025-10-06 | Check-in | 15:00 | 15:32 | 0:32 | Check-in 1: Met with group & Tyler, discussed our design draft, and asked questions regarding design plan and material buying
2025-10-12 | Logistics | 20:12 | 20:37 | 0:25 | Set-up GitHub updates on the group Discord to record team-members’ commits
2025-10-14 | Check-in | 11:20 | 11:51 | 0:31 | Check-in 2: Met with group & Tyler, reviewed out submitted design draft, discussed adding more hardware specification, and discussed with group members to start buying materials and beginning research
2025-10-18 | Design Plan | 22:09 | 23:39 | 1:30 | Made additions to the Hardware Specifications for the Design Plan and did research for the Bill of Materials in order to specify the hardware used and communication methods used
2025-10-19 | Design Plan | 17:55 | 19:38 | 1:43 | Made final edits to the Design Plan to complete and submit it with the group
2025-10-20 | Technical Research | 13:08 | 14:58 | 1:50 | Reviewed and added to the Bill of Materials and investigated basic Backend development concepts and different Database types and Data Storage structures (settled on MongoDB to store JSON data)
2025-10-20 | Check-in | 15:08 | 15:39 | 0:31 | Check-in 3: Met with group & Tyler, discussed Pre-Alpha Build and what is expected from it, and discussed with group members assignment of tasks and expectations from them for the Pre-Alpha Build.
2025-10-24 | Pre-Alpha Build | 15:12 | 21:17 | 6:05 | Created a skeleton-code backend with express.js and mongoose and a database to test the backend. Ran into issues due to original set up of backend code and MongoDB database not actually locally deployed.
2025-10-25 | Pre-Alpha Build | 11:49 | 17:14 | 5:25 | Updated backend to better organize functionality and finally got a MongoDB database set up locally on my laptop. Added CRUD functions to backend and successfully tested them with browser and Postman.
2025-10-25 | Technical Research | 18:24 | 18:54 | 0:30 | Researched how ESP-32 can communicate with Backend in order to send data to the database. Learned HTTP requests over Wifi can be used by ESP-32 with JSON format data to communicate with backend API.
2025-11-06 | Prototype | 10:35 | 14:39 | 4:04 | Made changes to the backend to allow for communication over Wifi via HTTP requests. Successfully tested communication between Frontend and Backend Server via HTTP and Wifi.
2025-11-11 | Prototype | 12:07 | 17:38 | 5:31 | Added a new JSON data model to be stored and interacted with on the database to successfully test HTTP requests from frontend to backend and display on frontend.
2025-11-13 | Prototype | 12:25 | 16:13 | 3:48 | Added port forwarding to my laptop to test slightly updated HTTP requests between frontend and backend. Helped in the development of functionality of ESP32 to send HTTP (POST) requests to the backend.
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00