## Sheet1
Name: | Aspen Boler |  | Total Time: | 31:29
Date: | General Category: | Starting Time: | Ending Time: | Calculated Time Worked: | Description:
2025-10-03 | Design Draft/Plans | 11:17 | 14:39 | 3:22 | Sat down with group after class to define project and talked through all of Design Draft points (Deliverables, Requirements, Division of work, ect.)
2025-10-04 | Design Draft | 10:17 | 11:55 | 1:38 | Researched and wrote description for the project's deliverable artifacts
2025-10-04 | Check-in | 17:05 | 17:35 | 0:30 | Reserved time slots for all of the group check-ins for Senior Design 1
2025-10-05 | Design Draft | 18:14 | 20:30 | 2:16 | Helped rework design draft to fit within word limit
2025-10-06 | Check-in | 15:00 | 15:32 | 0:32 | Check-in 1: Met with group & Tyler, discussed our design draft, and asked questions regarding design plan and material buying
2025-10-10 | GitHub Creation | 10:35 | 11:31 | 0:56 | Created repository, added members, created Project page, and created reports directory
2025-10-12 | Webhook Set-up | 20:15 | 20:31 | 0:16 | Helped Nicholas, according to research done by Carter Kreis, to set up and test Webhook so GitHub pushes would send to a discord channel
2025-10-14 | Check-in | 11:20 | 11:51 | 0:31 | Check-in 2: Met with group & Tyler, reviewed out submitted design draft, discussed adding more hardware specification, and discussed with group members to start buying materials and begin research
2025-10-17 | Timesheet | 15:00 | 16:00 | 1:00 | Created Timesheet template for all members
2025-10-20 | Check-in | 15:00 | 15:32 | 0:32 | Check-in 3: Met with group & Tyler, discussed things to prepare for alpha build completion and resources to buy
2025-10-24 | Research | 10:58 | 13:43 | 2:45 | Began researching ESP32-Wroom and how to develop code; Found IDF with example/interfaces and made into submodule; Used submodule to configure ESP_IDF on Vscode and examine example projects
2025-10-24 | Pre-Alpha Dev. | 14:30 | 21:17 | 6:47 | Flashed onto all three ESP32's, helped members install development on computers, defined structure for Sunday's end, created main skeleton, investigated examples to create hardware drivers
2025-10-25 | Pre-Alpha Dev. | 10:00 | 16:25 | 6:25 | Began writing report, determined how to integrate ADC into main alongside Fernando, began creating ADC peripheral interface and editted CMakeList.txt to include it after several attempts, tried to create ADC structure to center ADC initialization in one function but failed.
2025-10-25 | Pre-Alpha Dev. | 20:26 | 21:50 | 1:24 | Reviewed and editted cleaned up code/ReadMe, adjusted report
2025-10-26 | Pre-Alpha Dev. | 11:00 | 12:00 | 1:00 | Record and edit microprocessor portion of video
2025-10-26 | Pre-Alpha Dev. | 15:50 | 16:25 | 0:35 | Clean up readme and edit in frontend portion of video
2025-10-28 | Check-in | 11:20 | 11:50 | 0:30 | Check-in 4: Met with group & Tyler, discussed how we needed to begin implementing communication for the prototype. Sat down with group and designated work to reach these goals.
2025-11-04 | Check-in | 11:20 | 11:50 | 0:30 | Check-in 5: Met with group & Tyler, discussed work that was completed and set up group work day for following Thursday. Also discussed what work would be completed to meet goals and beginning communication and test sensors.
2025-11-06 | Prototype Dev. |  |  | 0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00